## Tasks Template
Phase Name | Task Title | Task Description | Priority | Estimate Hours
Planning | Initial site survey | Conduct comprehensive site survey and documentation | High | 8
| Feasibility study | Analyze technical and financial feasibility | High | 16
| Create project timeline | Develop detailed project schedule with milestones | Medium | 4
| Budget estimation | Prepare detailed cost estimates and budget breakdown | High | 12
Design | Conceptual design | Create initial design concepts and mood boards | High | 24
| Technical drawings | Prepare detailed technical and construction drawings | Critical | 40
| Material selection | Select and specify all materials and finishes | Medium | 16
| 3D visualization | Create 3D renders and walkthrough animations | Medium | 20
Procurement | Vendor selection | Research and select qualified vendors | High | 12
| Purchase orders | Create and process all purchase orders | Medium | 8
| Material tracking | Track delivery schedules and material arrival | Low | 4
| Quality verification | Verify material quality and specifications | High | 8
Construction | Site preparation | Prepare site for construction work | High | 16
| Demolition work | Remove existing structures and fixtures | Medium | 24
| Structural work | Complete all structural modifications | Critical | 80
| MEP installation | Install mechanical, electrical, and plumbing systems | Critical | 120
| Finishes installation | Install all finishes, fixtures, and fittings | High | 60
| Quality inspection | Conduct quality checks and punch list items | High | 16
Handover | Final inspection | Complete final walkthrough and inspection | Critical | 8
| Documentation | Prepare and submit all project documentation | High | 12
| Training | Train client staff on systems and maintenance | Medium | 8
| Warranty setup | Setup warranty tracking and support system | Low | 4

## Instructions
How to Use This Template
1. PHASE NAME (Column A):
- Enter the name of your project phase
- You can merge cells for multiple tasks in the same phase
- Or simply repeat the phase name for each task in that phase
2. TASK TITLE (Column B) - REQUIRED:
- Clear, concise name for the task
- This field is mandatory
3. TASK DESCRIPTION (Column C) - Optional:
- Detailed description of what needs to be done
- Include any important notes or requirements
4. PRIORITY (Column D) - Optional:
- Valid values: Low, Medium, High, Critical
- Default: Medium (if left blank)
5. ESTIMATE HOURS (Column E) - Optional:
- Numeric value only
- Estimated time to complete the task in hours
TIPS:
- Leave blank rows between phases for better readability (they will be ignored)
- You can add as many phases and tasks as needed
- Priority values are case-insensitive
- Invalid data will be flagged during upload with warnings
EXAMPLE:
Planning ¦ Initial survey ¦ Visit site and document current state ¦ High ¦ 8
Planning ¦ Create timeline ¦ Develop project schedule ¦ Medium ¦ 4
Design ¦ Concept design ¦ Create initial design concepts ¦ High ¦ 24
Design ¦ Technical drawings ¦ Prepare construction drawings ¦ Critical ¦ 40